## Cover
PATHWAYS |  | [Organization name]
MIDTERM REPORT
Coastal Livelihoods Project
1 Oct 2025 to 30 Sep 2026
CLP-2025-03 ¦ Borongan, Guiuan, Salcedo and Mercedes, Eastern Samar
Prepared for | Programme donor and board of trustees
Prepared by | M&E Officer, Coastal Livelihoods Project
Version | v1.0
Status | Draft
Generated | 2026-10-07 10:42
Confidentiality | Internal
Contents and section choices: Contents sheet. How the template works: Guide sheet.

## About
PATHWAYS ¦ CLP-2025-03 Coastal Livelihoods Project ¦ Midterm report
About this report
Fixed section. Always present. States what the report covers so readers can trust and reuse the numbers.
Item | Value
Organization | [Organization name]
Project title | Coastal Livelihoods Project
Project code | CLP-2025-03
Report preset | Midterm
Report period start | 2025-10-01
Report period end | 2026-09-30
Data cut-off | 2026-09-30
Project start | 2025-10-01
Project end | 2027-09-30
Timeline elapsed | 49.93%
Filter: location | All municipalities
Filter: indicator types | All
Filter: beneficiary segment | All (aggregates only)
Data sources | Verified activity updates, indicator measurements, released beneficiary aggregates, approved expenses, signed-off evaluation, approved evidence
Privacy | Beneficiary figures are aggregates only. Any group under 5 people shows as "Fewer than 5". No names or contact details appear in this report.
Generated | 2026-10-07 10:42
Sections included | 10 of 13 optional sections, plus the fixed sections
Note on B8: Pick a preset. It sets which sections are required on the Contents sheet.

## Contents
PATHWAYS ¦ CLP-2025-03 Coastal Livelihoods Project ¦ Midterm report
Contents
Fixed section. Set Include to Yes or No; numbering updates on every section sheet.
No. | Section | Sheet | Preset rule | Include | Check
| Cover | Cover | Always | Yes
| About this report | About | Always | Yes
1 | Executive summary | 1 Summary | Required | Yes | OK
2 | Project background | 2 Background | Default | Yes | OK
3 | Status overview | 3 Status | Default | Yes | OK
4 | Results and indicator performance | 4 Indicators | Default | Yes | OK
5 | Activities and milestones | 5 Activities | Default | Yes | OK
6 | Beneficiary reach | 6 Reach | Default | Yes | OK
- | Survey and assessment results | 7 Assessment | Optional | No | OK
7 | Financial summary | 8 Budget | Default | Yes | OK
8 | Evaluation | 9 Evaluation | Default | Yes | OK
9 | Risks, issues and decisions | 10 Risks | Default | Yes | OK
10 | Lessons learned and next steps | 11 Lessons | Default | Yes | OK
- | Annex: Means of verification | A Evidence | Optional | No | OK
- | Annex: Data tables | B Data tables | Optional | No | OK
A | Annex: Definitions and method | C Definitions | Always | Yes
| Sign-off | Sign-off | Always | Yes

## 1 Summary
PATHWAYS ¦ CLP-2025-03 Coastal Livelihoods Project ¦ Midterm report
1 Executive summary
Required in every preset. Status and key figures are computed; the summary text is editable.
Overall status | At risk | Worst status across Schedule, Budget, Indicators and Reach
Key figures
Figure | Value | Detail | Gap vs timeline
Timeline elapsed | 49.93% | 1 Oct 2025 to 30 Sep 2027
Budget used | 46% | PHP 5,520,000 of 12,000,000 | -3.931%
KPI achievement | 46.5% | Average progress across indicators | -3.431%
Beneficiaries reached | 742 | 62% of 1,200 target | 11.9%
Data-drafted summary (computed)
As of 30 Sep 2026, the project is 50% through its timeline, has used 46% of its approved budget, has reached 742 beneficiaries (62% of target), and averages 47% progress across its indicators.
Executive summary (editable)
[Copy the computed summary above, then add the one achievement and the one risk the reader must know, and what the project will do about the risk.]

## 2 Background
PATHWAYS ¦ CLP-2025-03 Coastal Livelihoods Project ¦ Midterm report
2 Project background
Auto section with one editable block. Source: project record.
Item | Detail
Project code | CLP-2025-03
Project title | Coastal Livelihoods Project
Status | Ongoing
Sector | Livelihoods and economic empowerment
Implementation area | Borongan, Guiuan, Salcedo and Mercedes, Eastern Samar
Start date | 2025-10-01
End date | 2027-09-30
Implementing partners | Two municipal LGUs and one cooperative federation
Program manager | Program Manager (role shown, not name)
Target beneficiaries | 1200
Objectives
Increase household income of coastal women through skills training, savings groups and start-up support for small enterprises, so families depend less on seasonal fishing.

## 3 Status
PATHWAYS ¦ CLP-2025-03 Coastal Livelihoods Project ¦ Midterm report
3 Status overview
Auto section. Status is computed by the rules in Annex C; the comment column is editable.
Area | Status | Basis | Comment
Schedule | At risk | Longest overdue milestone: 18 days | Kit procurement batch 2 delayed by supplier stock-out.
Budget | On track | 46% used vs 50% of timeline elapsed | Spend follows the work plan.
Indicators | On track | Average indicator progress 47% vs 50% elapsed | Outcome indicators lag until enterprises mature.
Reach | On track | 62% of target reached vs 50% elapsed | Cohort 3 enrolment opens in November.
Status rules: Annex C Definitions and method.

## 4 Indicators
PATHWAYS ¦ CLP-2025-03 Coastal Livelihoods Project ¦ Midterm report
4 Results and indicator performance
Auto section. Progress and status are computed; write a variance explanation for every indicator not On track.
Code | Indicator | Type | Unit | Baseline | Target | Current | Progress | Status | Variance explanation
OC1 | Trained women reporting higher monthly household income | Outcome | percent | 0% | 60% | 22% | 36.67% | At risk | [Explain the gap and the corrective action with a date.]
OC2 | Women-led enterprises operating 6 months after start-up | Outcome | number | 0 | 150 | 35 | 23.33% | Off track | [Explain the gap and the corrective action with a date.]
OP1 | Women completing livelihood skills training | Output | number | 0 | 900 | 612 | 68% | On track
OP2 | Savings groups formed and registered | Output | number | 0 | 40 | 26 | 65% | On track
OP3 | Start-up kits distributed | Output | number | 0 | 300 | 118 | 39.33% | At risk | Batch 2 delayed by a supplier stock-out; 82 kits due for distribution in October.
AC1 | Activity completion (derived) | Activity | percent | 0% | 100% | 46.67% | 46.67% | On track
KPI achievement (average indicator progress) | [6 empty] | 46.5% | On track
Source: indicator measurements and derived activity completion, 1 Oct 2025 to 30 Sep 2026. Status compares progress with timeline elapsed (50%).
Note on G11: Derived: linked to activity completion on 5 Activities.

## 5 Activities
PATHWAYS ¦ CLP-2025-03 Coastal Livelihoods Project ¦ Midterm report
5 Activities and milestones
Auto section. Status and days overdue are computed against the data cut-off.
Milestone | Target date | Completion date | Status | Days overdue | Note
Baseline survey completed | 2025-12-15 | 2025-12-12 | Completed | 0
Cohort 1 training completed | 2026-03-31 | 2026-03-31 | Completed | 0
Savings groups registered with LGU | 2026-06-30 | 2026-07-05 | Completed late | 0 | LGU session moved by one week.
Start-up kit procurement, batch 2 | 2026-09-12 |  | Overdue | 18 | Supplier stock-out; extension approved to 31 Oct 2026.
Midterm review workshop | 2026-10-20 |  | Planned | 0
Activity summary
Activities planned | 30
Activities completed | 14
Activity completion | 46.67%
Longest overdue milestone (days) | 18
Delays and extension requests
1 overdue explanation filed (kit procurement, supplier stock-out). 1 extension request approved: batch 2 distribution moved to 31 Oct 2026.
Source: project milestones, verified activity updates, overdue explanations and extension requests.

## 6 Reach
PATHWAYS ¦ CLP-2025-03 Coastal Livelihoods Project ¦ Midterm report
6 Beneficiary reach
Auto section, aggregates only. Groups under 5 are suppressed and never shown as zero.
Dimension | Category | People | Share
Sex | Female | 618 | 83.29%
| Male | 120 | 16.17%
| Not recorded | Fewer than 5 | -
Age | 18 to 24 | 131 | 17.65%
| 25 to 39 | 344 | 46.36%
| 40 to 59 | 228 | 30.73%
| 60 and over | 39 | 5.256%
Disability | With disability | 46 | 6.199%
| Without disability | 689 | 92.86%
| Not recorded | 7 | 0.9434%
Location | Borongan | 248 | 33.42%
| Guiuan | 201 | 27.09%
| Salcedo | 167 | 22.51%
| Mercedes | 126 | 16.98%
Total reached | Released aggregate | 742 | 100%
Source: released beneficiary aggregates (SADDD). Shares use the released total; suppressed groups are excluded from shares.
Journey stage progression
Stage |  | People | Of registered
Registered |  | 980 | 100%
Enrolled |  | 742 | 75.71%
Training completed |  | 612 | 62.45%
Enterprise started |  | 118 | 12.04%
Operating at 6 months |  | 35 | 3.571%
Reach against target |  | 61.83% | of 1,200 target

## 7 Assessment
PATHWAYS ¦ CLP-2025-03 Coastal Livelihoods Project ¦ Midterm report
[Not included] Survey and assessment results
Conditional section: included only when published assessment results exist for the period.
Assessment | Matched pairs | Pre-test mean | Post-test mean | Gain (points)
Enterprise basics and bookkeeping | 588 | 54.2 | 76.8 | 22.6
Source: pre-test and post-test results for participants with both scores.
Interpretation
[What does the gain mean for the outcome indicators?]

## 8 Budget
PATHWAYS ¦ CLP-2025-03 Coastal Livelihoods Project ¦ Midterm report
7 Financial summary
Auto section. Spent counts verified and approved expenses only.
Category | Approved budget (PHP) | Spent (PHP) | Used | Balance (PHP) | Used minus timeline
Training and capacity building | 3200000 | 1940000 | 60.62% | 1260000 | 10.69%
Start-up kits | 4500000 | 1310000 | 29.11% | 3190000 | -20.82%
Personnel | 2400000 | 1250000 | 52.08% | 1150000 | 2.152%
Monitoring and evaluation | 900000 | 520000 | 57.78% | 380000 | 7.846%
Administration and logistics | 1000000 | 500000 | 50% | 500000 | 0.06859%
Total | 12000000 | 5520000 | 46% | 6480000 | -3.931%
Pending expenses (excluded from Spent)
Count | 3
Amount (PHP) | 184500
Source: approved project budget records and expense entries with VERIFIED or APPROVED status.
Financial commentary
Start-up kit spend is low because batch 2 is delayed; it should reach about 50% once the October distribution is paid. [Note any planned budget realignment.]

## 9 Evaluation
PATHWAYS ¦ CLP-2025-03 Coastal Livelihoods Project ¦ Midterm report
8 Evaluation
Conditional section: included only when a signed-off or archived evaluation exists for the period.
Criterion | Weight | Score | Maximum | Weighted score
KPI achievement | 30% | 3 | 5 | 0.9
Timeline compliance | 20% | 4 | 5 | 0.8
Budget efficiency | 20% | 4 | 5 | 0.8
Beneficiary reach | 20% | 4 | 5 | 0.8
Assessment gain | 10% | 5 | 5 | 0.5
Overall | 100% |  | 5 | 3.8
Overall percent |  |  |  | 76%
Weights total 100%
Source: midterm evaluation, signed off 30 Sep 2026.

## 10 Risks
PATHWAYS ¦ CLP-2025-03 Coastal Livelihoods Project ¦ Midterm report
9 Risks, issues and decisions
Conditional section: open alerts and decisions come from the rules engine; add other risks in the yellow rows.
Type | Item | Severity or status | Mitigation or next step
Alert | Start-up kit distribution behind schedule | High | Local supplier sourced for batch 3.
Alert | Enterprise survival indicator below trajectory | Medium | [Mitigation]
Decision | Source kit batch 3 from a local supplier | Approved | Contract signed 28 Sep 2026.
Decision | Add mentoring visits in enterprise months 3 to 6 | Proposed | [Next step]
Other risk | [Risk not raised by system alerts] | [Severity] | [Mitigation]
Other risk
Source: open rule-based alerts (highest severity first, up to 10) and decision recommendations.

## 11 Lessons
PATHWAYS ¦ CLP-2025-03 Coastal Livelihoods Project ¦ Midterm report
10 Lessons learned and next steps
Narrative section. All blocks are editable.
Challenges
[What slowed the project down this period?]
Lessons learned
Savings groups formed faster where barangay officials co-hosted the first meeting.
Recommendations
[What should management or the donor change?]
Next-period priorities
Distribute 82 batch-2 kits by 31 Oct 2026; open Cohort 3 enrolment; start enterprise mentoring visits.

## A Evidence
PATHWAYS ¦ CLP-2025-03 Coastal Livelihoods Project ¦ Midterm report
[Not included] Means of verification
Auto annex. Only approved evidence appears; identifying items are listed, never shown as images.
Ref | Evidence | Type | Supports | Date | Identifying | In PDF and DOCX
EV-0412 | Attendance sheets, Cohort 2 training | Document | OP1 | 2026-08-14 | No | Listed
EV-0388 | Savings group registration certificates | Document | OP2 | 2026-07-05 | No | Listed
EV-0455 | Kit distribution, Guiuan | Photo | OP3 | 2026-09-02 | No | Shown as thumbnail
EV-0461 | Outcome monitoring survey summary | Document | OC1 | 2026-09-25 | No | Listed
EV-0470 | Enterprise owner at her stall | Photo | OC2 | 2026-09-27 | Yes | Listed only
Source: approved evidence media linked to indicators and activities in the report period.

## B Data tables
PATHWAYS ¦ CLP-2025-03 Coastal Livelihoods Project ¦ Midterm report
[Not included] Data tables
Auto annex. PATHWAYS adds the full tables behind each included section here when exporting.
- Indicator measurement history (every period value and correction)
- All activities with planned and actual dates, progress and beneficiaries per session
- Expense totals by month and category
- Survey item results (respondents, answered, missing, mean)

## C Definitions
PATHWAYS ¦ CLP-2025-03 Coastal Livelihoods Project ¦ Midterm report
Annex A Definitions and method
Fixed annex. Always present.
Term | Definition
Status: Schedule | Off track when a milestone is more than 30 days overdue; at risk when any milestone is overdue.
Status: Budget | Off track above 100% used; at risk when budget used runs more than 15 points ahead of timeline elapsed.
Status: Indicators | At risk when progress is more than 10 points behind timeline elapsed; off track when more than 25 behind.
Status: Reach | Same thresholds as Indicators, using reach against target.
Timeline elapsed | Days from project start to the data cut-off, divided by the project's total days.
Progress | (Current - Baseline) / (Target - Baseline).
Not available | A value could not be computed from verified records. It is never shown as zero.
Fewer than 5 | A group too small to report without risk of identifying people.
Derived indicator | Calculated by PATHWAYS from records, such as activity completion, rather than entered by hand.

## Sign-off
PATHWAYS ¦ CLP-2025-03 Coastal Livelihoods Project ¦ Midterm report
Sign-off
Editable. Fill in before sharing the final version.
Step | Name | Position | Date | Signature
Prepared by
Reviewed by
Approved by

## Guide
PATHWAYS ¦ CLP-2025-03 Coastal Livelihoods Project ¦ Midterm report
Template guide
How this template works. PATHWAYS fills the blue cells when a report is generated; people write in the yellow cells.
Cell legend
Yellow fill | Editable. Write or replace the text; starter text and [prompts] are suggestions.
Blue fill | System data. Filled by PATHWAYS from verified records at generation; sample values are fictional.
No fill | Formula or fixed text. Computed from other cells; do not overwrite.
Grey italic | Fixed wording that must stay, such as definitions and privacy notices.
Steps
1. On About, pick the report preset, period and filters.
2. On Contents, set Include to Yes or No per section. Required sections must stay Yes; the Check column flags mistakes.
3. Excluded sections renumber automatically; their sheets show [Not included] and are skipped on export.
4. Write the yellow narrative cells, starting with the Executive summary and the variance explanations.
5. Never type over a blue or formula cell; regenerate the report in PATHWAYS if the numbers are wrong.
Sections by preset
Required = locked on. Default = on unless removed. Optional = off unless added. Not offered = hidden in that preset.
Section | Sheet | Midterm | Evidence (M&E) | Quarterly progress | Final | Donor brief
Cover overline |  | MIDTERM REPORT | EVIDENCE REPORT | QUARTERLY PROGRESS REPORT | END-OF-PROJECT REPORT | DONOR BRIEF
1 Executive summary | 1 Summary | Required | Required | Required | Required | Required
2 Project background | 2 Background | Default | Optional | Optional | Default | Default
3 Status overview | 3 Status | Default | Default | Default | Default | Default
4 Results and indicator performance | 4 Indicators | Default | Required | Default | Default | Default
5 Activities and milestones | 5 Activities | Default | Default | Default | Default | Optional
6 Beneficiary reach | 6 Reach | Default | Default | Default | Default | Default
7 Survey and assessment results | 7 Assessment | Optional | Default | Optional | Default | Optional
8 Financial summary | 8 Budget | Default | Optional | Default | Default | Default
9 Evaluation | 9 Evaluation | Default | Optional | Not offered | Required | Optional
10 Risks, issues and decisions | 10 Risks | Default | Optional | Default | Optional | Not offered
11 Lessons learned and next steps | 11 Lessons | Default | Optional | Default | Default | Optional
Annex A Means of verification | A Evidence | Optional | Required | Optional | Default | Not offered
Annex B Data tables | B Data tables | Optional | Default | Optional | Default | Not offered
Default period |  | Project start to midpoint | Last quarter | Last quarter | Whole project | Project start to report date
Always present
- Cover, About this report, the Executive summary status and key figures, Annex C Definitions and method, and the Sign-off block.
- A section the user has no access to is left out without comment.
- A selected section with no records stays in and says so, for example "No milestones in this period."
- Groups under 5 people show "Fewer than 5". A missing value shows "Not available", never zero.
- Every table carries a source line naming the records and the period.
Export formats
- PDF: the designed document, one section per heading, charts included.
- DOCX: the same headings as Word styles so the contents page and every block can be edited.
- XLSX: this workbook, with only the included section sheets.
- CSV: one row per value (section, table, item, category, value, unit, metric state, reason).